## project
Mr. Pour: Schedule

Chris Eustis					Plan		Actual		% Complete			Actual (beyond plan)				% Complete (beyond plan)
Slater Claudel
	PLAN	PLAN	ACTUAL	ACTUAL	PERCENT	TEAM		Months (January 2015 - May 2016)
ACTIVITY	START	DURATION	START	DURATION	COMPLETE	MEMBER		Jan '15	Feb '15	Mar '15	Apr '15	May '15	June '15	July '15	Aug '15	Sept '15	Oct '15	Nov '15	Dec '15	Jan '16	Feb '16	Mar '16	Apr '16	May '16
					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17
Project idea	1	1	1	1	100%	BOTH
Discover parts needed	1	3	1	4	100%	BOTH
ECE 405 documents	1	4	1	4	100%	BOTH
Preliminary design	1	5	1	5	100%	BOTH
Preliminary testing	2	10	2	10	100%	BOTH
Interface pumps for controlling liquid	8	2	8	3	100%	CE
Interace modules for cooling	8	2	8	2	100%	CE
Interface temperature sensor	8	2	8	2	100%	CE
Interface display	8	3	8	3	100%	SC
ECE 406 progress report 1	9	1	9	1	100%	BOTH
Parts Order # 1 - 9/18/2015	9	1	9	1	100%	BOTH
Assemble components together	9	4	10	3	100%	BOTH
ECE 406 progress report 2	10	1	10	1	100%	BOTH
Parts Order # 2 - 10/9/2015	10	1	10	1	100%	BOTH
PCB Order - 10/26/2015	10	1	10	1	100%	BOTH
Develop interface for display	10	2	10	2	100%	SC
Construction of container	10	2	10	2	100%	CE
Test pouring against specs	10	2	10	2	100%	SC
Test temperature control against specs	10	2	10	2	95%	SC
Test display against specs	10	2	10	2	100%	CE
Formulate Temperature Proof	11	2	11	2	100%	SC
ECE 406 progress report 3	11	1	11	1	100%	BOTH
Qualifiers week	11	1	11	1	100%	BOTH
Design review	12	5	0	0	0%	BOTH
ECE 403 presentation	13	3	0	0	0%	BOTH
ECE 403 report	13	4	0	0	0%	BOTH