## project
Mr. Pour: Schedule
Chris Eustis | [7 empty] | Plan |  | Actual |  | % Complete |  |  | Actual (beyond plan) |  |  |  | % Complete (beyond plan)
Slater Claudel
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | TEAM | Months (January 2015 - May 2016)
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | MEMBER | Jan '15 | Feb '15 | Mar '15 | Apr '15 | May '15 | June '15 | July '15 | Aug '15 | Sept '15 | Oct '15 | Nov '15 | Dec '15 | Jan '16 | Feb '16 | Mar '16 | Apr '16 | May '16
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Project idea | 1 | 1 | 1 | 1 | 100% | BOTH
Discover parts needed | 1 | 3 | 1 | 4 | 100% | BOTH
ECE 405 documents | 1 | 4 | 1 | 3 | 100% | BOTH
Preliminary design | 1 | 5 | 1 | 4 | 100% | BOTH
Preliminary testing | 2 | 10 | 2 | 8 | 40% | BOTH
Interface pumps for controlling liquid | 8 | 2 | 0 | 0 | 20% | CE
Interace modules for cooling | 8 | 2 | 0 | 0 | 0% | CE
Interface temperature sensor | 8 | 2 | 0 | 0 | 0% | CE
Interface display | 8 | 3 | 0 | 0 | 10% | SC
ECE 406 progress report 1 | 9 | 1 | 0 | 0 | 30% | BOTH
Parts Order # 1 - 9/18/2015 | 9 | 1 | 0 | 0 | 30% | BOTH
Assemble components together | 9 | 4 | 0 | 0 | 5% | BOTH
ECE 406 progress report 2 | 10 | 1 | 0 | 0 | 0% | BOTH
Parts Order # 2 - 10/9/2015 | 10 | 1 | 0 | 0 | 0% | BOTH
PCB Order - 10/26/2015 | 10 | 1 | 0 | 0 | 0% | BOTH
Develop interface for display | 10 | 2 | 0 | 0 | 0% | SC
Construction of container | 10 | 2 | 0 | 0 | 15% | CE
Test pouring against specs | 10 | 2 | 0 | 0 | 0% | SC
Test temperature control against specs | 10 | 2 | 0 | 0 | 0% | SC
Test display against specs | 10 | 2 | 0 | 0 | 0% | CE
ECE 406 progress report 3 | 11 | 1 | 0 | 0 | 0% | BOTH
Qualifiers week | 11 | 1 | 0 | 0 | 0% | BOTH
Design review | 12 | 5 | 0 | 0 | 0% | BOTH
ECE 403 presentation | 13 | 3 | 0 | 0 | 0% | BOTH
ECE 403 report | 13 | 4 | 0 | 0 | 0% | BOTH